# 📘 PMG201c – Practical Exam 2 (Summer 2025)

Select a project from the university training subjects or university activities that you are currently working on, have worked on in the past or a relevant project from your friend/relative that you know, give the solutions or answers for following requests based on your understanding about the project and assumptions.

## Request 1 (20%)

Develop a narrative charter statement that includes the following details:

- Project name

- Project purpose or justification

- High level requirements (at least two)

## Request 2 (20%)

Provide at least five main cost/budget items.
For each item, provide:

- Name

- Description

- Estimation

- How to estimate (method)

- Person in charge

## Request 3 (30%)

Develop a communication plan for the project where you:

- Define at least three project stakeholders (project–internal, organization–internal, external)

- Create a communication plan for each stakeholder including:

  - Information

  - Purpose

  - Frequency

  - Method/Format

  - Responsible person

## Request 4 (30%)

Provide at least three main project milestones used to mark project progress.
Select one milestone → list at least ten activities → identify sequence relationships (FS, SS, FF, SF) among them.

# ✅ FULL ANSWER — SOLUTION

# ✅ REQUEST 1 – Narrative Charter Statement (20%)

- Project Name
Smart Learning & Auto-Exam Generation System

- Project Purpose / Justification
The purpose of this project is to support students in exam preparation by automating the extraction of study materials and generating structured practice questions. Students often struggle with managing large amounts of content, summarizing documents, and manually creating revision questions. This system provides document scanning, OCR-based text extraction, and automated question generation to reduce preparation time and increase study efficiency.

- High-Level Requirements
1. Document Scanning & Text Extraction
The system must allow users to upload or scan PDFs/images and extract readable text automatically using OCR technology.

2. Auto Question Generation
The system must generate multiple-choice or short-answer questions from extracted text using predefined templates or AI-driven question-generation logic.

# ✅ REQUEST 2 – Five Cost / Budget Items (20%)

1. OCR Engine Cost
• Description: Payment for OCR API usage to process scanned documents.
• Estimation: Approx. $8,000 for one academic year.
• How to Estimate: Based on projected number of pages × API price per page.
• Person in Charge: AI/OCR Engineer.

2. Developer Labor Cost
• Description: Compensation for frontend, backend, and AI developers.
• Estimation: Approx. $45,000 for full development duration.
• How to Estimate: Monthly salary rate × number of months × number of developers.
• Person in Charge: Project Manager.

3. Cloud Infrastructure Cost
• Description: Hosting servers, storage for uploaded documents, and processing power.
• Estimation: Around $6,000 for development + deployment period.
• How to Estimate: Use cloud provider cost calculator (AWS/Azure).
• Person in Charge: DevOps Engineer.

4. Testing & QA Tools Cost
• Description: Tools for functional testing, performance testing, and bug tracking.
• Estimation: Approximately $2,000.
• How to Estimate: Based on subscription fees from selected QA tools.
• Person in Charge: QA/Test Lead.

5. UI/UX Design Cost
• Description: Designing wireframes, user interfaces, prototypes, and visual elements.
• Estimation: About $3,000.
• How to Estimate: Designer hourly rate × estimated design hours.
• Person in Charge: UI/UX Designer.

# ✅ REQUEST 3 – Communication Plan (30%)

### Stakeholder 1 – Development Team (Project-internal)

• Information: Technical tasks, updates, blocker issues.
• Purpose: Ensure alignment and smooth collaboration.
• Frequency: Weekly + as needed.
• Method/Format: Meetings, Slack/Teams messages.
• Responsible Person: Project Manager.

### Stakeholder 2 – Academic Department (Organization-internal)

• Information: Progress updates, demo versions, feature validation.
• Purpose: Confirm system meets academic requirements.
• Frequency: Bi-weekly.
• Method/Format: Email summary + live demo sessions.
• Responsible Person: Project Manager.

### Stakeholder 3 – OCR Technology Vendor (External)

• Information: Error reports, performance issues, API requests.
• Purpose: Maintain stable OCR service support.
• Frequency: As issues occur.
• Method/Format: Email + support ticket system.
• Responsible Person: AI Engineer.

# ✅ REQUEST 4 – Milestones + Activities + Sequence Relationships (30%)

### Three Main Project Milestones

- Completion of Requirements & System Design

- Completion of OCR & Question-Generation Module

- Completion of System Deployment & User Acceptance Testing

### Selected Milestone:

Milestone 2 – OCR & Question-Generation Module Completion

Below are the minimum 10 activities and their sequence relationships:

- A – Review functional requirements
→ Must finish before B (FS)

- B – Design OCR architecture
→ Starts after A is finished (FS)

- C – Build OCR preprocessing logic
→ Starts after B (FS)

- D – Implement OCR extraction module
→ Starts after C (FS)

- E – Conduct OCR accuracy testing
→ Starts after D (FS)

- F – Design question-generation templates
→ Can start at the same time as C (SS)

- G – Develop question-generation algorithm
→ Starts after F is finished (FS)

- H – Integrate OCR module with question generator
→ Starts when both E and G are finished (FS)

- I – Perform integration testing
→ Starts after H (FS)

- J – Approve and close milestone
→ Starts after I (FS)

Note:

### 1. FS – Finish to Start

Activity A phải kết thúc rồi Activity B mới được bắt đầu.
→ Đây là quan hệ phổ biến nhất (khoảng 90% dự án dùng FS).

Ví dụ:
“Thiết kế xong (finish) → mới được code (start)”.

### 2. SS – Start to Start

A và B có thể bắt đầu cùng lúc, hoặc B bắt đầu sau A một chút.

Ví dụ:
“Viết template câu hỏi” và “xử lý OCR” có thể bắt đầu cùng lúc.

### 3. FF – Finish to Finish

A và B phải kết thúc cùng thời điểm, hoặc một task kết thúc kéo theo task kia kết thúc.

Ít dùng.
Ví dụ:
“Kết thúc kiểm thử hiệu năng” cùng lúc với “kết thúc kiểm thử bảo mật”.

### 4. SF – Start to Finish

A bắt đầu thì B mới được kết thúc → dạng hiếm, gần như không dùng trong bài thi.

Ví dụ:
Nhân viên mới làm ca → người cũ mới được về.