# PMG201c.PE1_University Library Digitalization Project

### Given the context for the project as following, you are the PM for this project

A university is undertaking a digitalization project to convert its entire library collection into a digital format. The system must allow students and faculty to search, view, and download books, research papers, and journals. The project includes:

- Scanning 50,000 books and 100,000 research papers

- Creating an AI search engine to retrieve content efficiently

- Implementing user authentication for controlled access

- Ensuring data security and backup

The project duration is 12 months, with a budget of $500,000. The university has hired an IT company to develop the software, and the library staff will be responsible for categorizing and verifying scanned content.

## Request 1 (weight 15%)

Define at least 2 project objectives using SMART criteria.

## Request 2 (weight 25%)

Define the scope for this project including:

- In-scope items

- Exclusive (out-of-scope) items

- Deliverables required for the project

## Request 3 (weight 25%)

Assume that you have defined and estimated schedule for one of the main project deliverables with the following activities:

| Activity | Preceding Activity | Duration (Weeks) |
| --- | --- | --- |
| Start | – | 0 |
| A | Start | 3 |
| B | A | 5 |
| C | B | 2 |
| D | B | 3 |
| E | B | 5 |
| F | C | 3 |
| G | D | 5 |
| H | D, E | 4 |
| I | F, G | 3 |
| End | H, I | 0 |

Questions:
a. What are the paths in the network diagram?
b. What is the minimum duration to complete the deliverable?
c. Which activities have the most flexibility (float)?

## Request 4 (weight 35%)

The university is digitalizing 50,000 books and 100,000 research papers. After 5 months, the project is behind schedule, having scanned only 15,000 books (30%) instead of the planned 25,000 (50%).
The AI search feature is incomplete, causing retrieval issues.

a. Evaluate project performance after 5 months (schedule + cost).
b. Suggest corrective actions to complete the project within the next 7 months.

━━━━━━━━━━━━━━━━━━

# ✅ GIẢI FULL – THEO ĐÚNG FORMAT BẠN YÊU CẦU

# ✅ REQUEST 1 – SMART Objectives (15%)

### 🎯 Objective 1: Complete the scanning of 50,000 books & 100,000 research papers

- Specific: Digitize all physical books and research papers in the library.

- Measurable: Total 150,000 items scanned and uploaded.

- Achievable: Supported by IT vendor + library staff.

- Relevant: Required to achieve full digital library transformation.

- Time-bound: Completed within 12 months.

### 🎯 Objective 2: Deploy an accurate AI Search Engine

- Specific: Build an AI-based search engine for retrieving scanned content.

- Measurable: Achieve ≥ 95% search relevance score in testing.

- Achievable: Within budget and available technical expertise.

- Relevant: Critical for user access and usability.

- Time-bound: Completed before project month 12.

━━━━━━━━━━━━━━━━━━

# ✅ REQUEST 2 – Project Scope (25%)

## 🔵 In-scope Items

- Development of the digital library web system

- OCR scanning of books and research papers

- AI search engine development

- User authentication & access control

- Cloud storage integration & backup system

- Data validation by library staff

- Deployment, testing & documentation

## 🔴 Out-of-scope Items

- Mobile app (iOS/Android)

- Multilingual UI support

- Integration with other universities

- Physical book restoration or reprinting

- Training students/faculty (handled by university IT)

## 🟢 Deliverables

- Fully functional digital library website

- AI search module (semantic + keyword search)

- OCR-scanned and categorized documents

- User authentication and access-control system

- Backup and recovery plan

- Test report + user guide + system documentation

- Final deployment and project closure report

━━━━━━━━━━━━━━━━━━

# ✅ REQUEST 3 – Network Diagram Analysis (25%)

## a. All project paths

1️⃣ Start → A → B → C → F → I → End
2️⃣ Start → A → B → D → G → I → End
3️⃣ Start → A → B → D → H → End
4️⃣ Start → A → B → E → H → End

## b. Minimum duration (critical path)

### Calculate durations:

- Path 1 = 3 + 5 + 2 + 3 + 3 = 16 weeks

- Path 2 = 3 + 5 + 3 + 5 + 3 = 19 weeks

- Path 3 = 3 + 5 + 3 + 4 = 15 weeks

- Path 4 = 3 + 5 + 5 + 4 = 17 weeks

👉 Critical Path = Path 2 = 19 weeks

## c. Activities with the most float

- Critical path activities: A, B, D, G, I → 0 float

- Float analysis shows:

  - C & F ≈ 1 week float

  - E & H ≈ 2 weeks float (most flexible)

👉 Most flexible activities: E and H

━━━━━━━━━━━━━━━━━━

# ✅ REQUEST 4 – Project Performance + Corrective Actions (35%)

## a. Schedule and cost performance at month 5

### Schedule

- Planned: 50% = 25,000 books

- Actual: 30% = 15,000 books

📉 Schedule Performance Index (SPI)
SPI = EV / PV = 0.30 / 0.50 = 0.60
→ Only 60% of planned work achieved.

📉 Schedule Variance (SV)
SV = EV – PV = 0.30 – 0.50 = –0.20 (–20%)
→ Behind schedule.

### Cost

No exact cost given → assume proportional.

Since scanning less work than planned →
→ Short-term cost underrun but
→ Long-term cost overrun risk because delays increase labor cost.

### AI Search feature incomplete

→ Scope risk
→ Quality risk
→ Might cause rework → cost & time increase.

## b. Corrective actions (to finish in next 7 months)

### 1. Increase scanning capacity

- Add 5–10 temporary scanning staff

- Extend working hours / shift work

- Rent additional scanners
📌 Objective: Boost output by 40–50% monthly.

### 2. Fast-track development

- Work on AI search engine and backend in parallel with scanning

- Overlap integration + testing phases
📌 Save 1–2 months.

### 3. Fix AI search feature early (front-load critical tasks)

- Resolve model issues immediately

- Avoid later bottleneck
📌 Prevent rework and final-stage delay.

### 4. Prioritize critical path tasks

- Focus resources on D → G → I chain
📌 Directly reduces final project duration.

### 5. Weekly progress tracking (EVM + KPI dashboard)

📌 Early detection of slippage → faster correction.

### 6. De-scope nonessential features

- Remove optional UI/UX enhancements

- Delay advanced analytics to Phase 2
📌 Protect delivery within 7 months.

━━━━━━━━━━━━━━━━━━