# PMG201c.PE2 – E-Commerce Website for Small Businesses

Given the context for the project as following, you are the PM for this project.

A company is launching a multi-vendor e-commerce platform for small businesses. The platform must provide:

- User registration for businesses to create their online stores.

- Payment integration with multiple payment providers.

- Product listing and order tracking features.

- Customer review system for feedback and ratings.

The website must support up to 10,000 vendors and 100,000 daily transactions. The project has 6 months to launch its first version, with a budget of $800,000.

## Request 1 (weight 15%)

Define at least 2 project objectives using SMART criteria (Specific, Measurable, Achievable, Relevant, Time-bound).

## Request 2 (weight 25%)

Define the scope for this project including:

- In-scope items

- Exclusive (out-of-scope) items

- Deliverables you need to provide for the project

## Request 3 (weight 25%)

Define at least five quality assurance (QA) or quality control (QC) activities for the project.
For each activity classify it as QA or QC and describe the purpose, when, and how to do it.

## Request 4 (weight 35%)

Given the activity table:

a. What are paths in the network diagram for the deliverable?
b. Identify the minimum duration to complete that deliverable.
c. Which activities have the most flexibility (float)?
d. In week 8, activity D is being executed and you need to recover a 3-week delay. Define at least four solutions with explanation.

# ✅ FULL SOLUTION

# ✅ REQUEST 1 – SMART Objectives

### Objective 1 – Launch MVP within 6 months

- Specific: Deliver core e-commerce functions: vendor registration, product listing, order tracking, customer reviews.

- Measurable: Must support 10,000 vendors and 100,000 daily transactions.

- Achievable: Development team and budget of $800,000 are available.

- Relevant: Core features enable business operations for small vendors.

- Time-bound: Completed within 6 months.

### Objective 2 – Implement secure multi-provider payment integration

- Specific: Integrate at least 3 payment gateways.

- Measurable: Payment success rate ≥ 98% under load.

- Achievable: APIs and technical resources available.

- Relevant: Payments are essential to platform operations.

- Time-bound: Must be completed by month 5.

# ✅ REQUEST 2 – Scope Definition

### 🔵 In-Scope Items

- Vendor registration & authentication

- Product management system

- Order placement and tracking

- Payment integration

- Customer review feature

- Admin dashboard

- Performance testing up to 100,000 transactions/day

- Security features (encryption, fraud detection)

### 🔴 Out-of-Scope Items

- Mobile app (Android/iOS)

- Social commerce integration

- AI recommendation engine

- Loyalty or reward programs

- Multi-language support

### 🟢 Deliverables

- Fully deployed e-commerce web platform

- Vendor management module

- Payment integration module

- Order and logistics tracking

- Customer review system

- Test reports (functional, performance, security)

- System documentation

- Deployment guide

# ✅ REQUEST 3 – QA/QC Activities

### 1. Requirements Review (QA)

- Purpose: Ensure requirements are complete and correct.

- When: Before design phase.

- How: Review sessions with stakeholders.

### 2. Design Review (QA)

- Purpose: Validate architecture scalability for 10,000 vendors.

- When: After design completion.

- How: Architecture walkthrough meeting.

### 3. Code Review (QC)

- Purpose: Detect coding errors and security issues early.

- When: During development.

- How: Peer review via Git pull requests.

### 4. Functional Testing (QC)

- Purpose: Ensure each feature works according to requirements.

- When: After each module is completed.

- How: Execute test cases.

### 5. Performance Testing (QC)

- Purpose: Validate system handles 100,000 daily transactions.

- When: Before UAT phase.

- How: Use load-testing tools (JMeter).

### 6. Security Testing (QC)

- Purpose: Protect user data, payment info.

- When: After integration.

- How: Penetration testing, vulnerability scanning.

# ✅ REQUEST 4 – Critical Path Analysis

## (a) All Paths

1️⃣ Start → A → B → C → G → End
2️⃣ Start → D → B → C → G → End
3️⃣ Start → D → E → F → G → End
4️⃣ Start → D → H → I → End

## (b) Minimum Duration (Critical Path)

### Path 1: 4 + 3 + 2 + 6 = 15 weeks

### Path 2: 5 + 3 + 2 + 6 = 16 weeks

### Path 3: 5 + 4 + 2 + 6 = 17 weeks

### Path 4: 5 + 5 + 9 = 19 weeks ⭐ Longest

➡️ Minimum Duration = 19 weeks
➡️ Critical Path = Path 4: Start → D → H → I → End

## (c) Activities with the Most Flexibility (Float)

Activities NOT on the critical path have float:

- A

- B

- C

- E

- F

- G

➡️ Most flexible activities: A, B, C, E, F

(G has minimal float because it appears in all noncritical paths)

## (d) Week 8 – Activity D is delayed 3 weeks → Solutions

### 1. Fast Tracking

- Start H earlier (overlap D & H).

- Works if parts of H do not depend on full completion of D.

### 2. Crashing

- Add more developers to speed up D or H.

- Reduces duration through additional manpower.

### 3. Overtime

- Work extended hours/weekends to recover the delay.

### 4. Reallocate Resources

- Move staff from float activities (A, C, E, F) to help with critical tasks (D, H, I).

- Does not impact total duration because these tasks have slack.

### 5. De-scope Noncritical Work (optional)

- Reduce low-priority tasks to free resources for critical path.