# 📘 COPY ĐỀ – PMG201c.PE3 – E-Commerce Website for Small Businesses

Given the context for the project as following, you are the PM for this project.

A company is launching a multi-vendor e-commerce platform for small businesses. The platform must provide:

- User registration for businesses to create their online stores.

- Payment integration with multiple payment providers.

- Product listing and order tracking features.

- Customer review system for feedback and ratings.

The website must support up to 10,000 vendors and 100,000 daily transactions.

## Request 1 (weight 20%)

Identify 4 stakeholders and their relevant influences on the project.
Define the strategy to manage each stakeholder.

## Request 2 (weight 20%)

Identify at least 4 significant risks that the project faces.
For each risk, determine:

- Probability

- Impact

- Relevant mitigation strategies

## Request 3 (weight 35%)

Given activity table:

a. What are paths in the network diagram?
b. Identify the minimum duration.
c. Which activities have the most flexibility (float)?
d. In the 5th day, you are executing activity D and you need to recover 3-day delay.
Provide at least 4 solutions with explanation and assumptions.

## Request 4 (weight 25%)

The project team has completed a workload equivalent to $300,000 and has spent $400,000 to date.
You were budgeted $500,000 for the work scheduled.
At the start, the project budget was $800,000 and the project needs 6 months to finish.

Evaluate the current project status and give forecast to complete the project in terms of schedule and cost.
Show detailed calculations.

# ✅ FULL SOLUTION – PMG201c.PE3

# ✅ REQUEST 1 – Stakeholders (20%)

### Stakeholder 1 – Senior Management

Influence: High power, high interest. Controls funding and final approval.
Strategy: Keep closely informed, provide weekly reports, early escalation of issues.

### Stakeholder 2 – IT Development Team

Influence: High interest, medium power. Directly builds the platform.
Strategy: Daily communication, clear requirement documents, collaborative problem-solving.

### Stakeholder 3 – Vendors (Small Businesses)

Influence: High interest, low power. Their usage determines system success.
Strategy: Provide beta testing access, collect feedback regularly, ensure usability.

### Stakeholder 4 – Payment Gateway Providers

Influence: Medium power, critical dependency.
Strategy: Maintain strong technical communication, validate integration early, secure SLAs.

# ✅ REQUEST 2 – Risks (20%)

### Risk 1 – Payment integration failure

- Probability: Medium

- Impact: High

- Mitigation: Test APIs early, ensure fallback provider, sandbox testing.

### Risk 2 – System overload from high traffic

- Probability: Medium

- Impact: High

- Mitigation: Conduct stress testing, scale using cloud auto-scaling.

### Risk 3 – Security breach / customer data exposure

- Probability: Low

- Impact: Very High

- Mitigation: Encryption, penetration testing, compliance checks.

### Risk 4 – Vendor onboarding delays

- Probability: Medium

- Impact: Medium

- Mitigation: Prepare onboarding tutorials, support team, automated vendor approval workflow.

# ✅ REQUEST 3 – Critical Path Analysis (35%)

### (a) All Possible Paths

Using activity dependencies:

1️.Start → A → B → C → H → End
2️.Start → A → B → F → G → End
3️.Start → D → E → I → End
4️.Start → D → G → End
5️.Start → A → B → F → G → End
6️.Start → A → B → C → H → End

(We condense identical paths; main distinct ones:)

✔ Path 1: Start–A–B–C–H–End
✔ Path 2: Start–A–B–F–G–End
✔ Path 3: Start–D–E–I–End
✔ Path 4: Start–D–G–End

### (b) Duration of Each Path

Path 1:
A(4) + B(5) + C(2) + H(8) = 19 weeks

Path 2:
A(4) + B(5) + F(7) + G(3) = 19 weeks

Path 3:
D(5) + E(3) + I(3) = 11 weeks

Path 4:
D(5) + G(3) = 8 weeks

### ⭐ Minimum Duration = 19 weeks

### ⭐ Critical Paths = Path 1 and Path 2

### (c) Activities With the Most Flexibility (Float)

Critical path tasks have 0 float:
A, B, C, H, F, G

Non-critical tasks have float:
✔ D
✔ E
✔ I

➡️ Activities with the most float: D, E, I

### (d) Recovering 3-day Delay in Activity D (Week 5)

Provide 4 solutions:

### 1. Fast-Tracking

Overlap D with E instead of waiting for D to finish fully.
Assumption: Some parts of E can start using partial output.

### 2. Crashing (Add more manpower)

Assign additional developers to D or E to shorten their durations.
Assumption: Task can be parallelized.

### 3. Overtime / Extended shifts

Increase daily working hours or add weekend work.
Assumption: Budget available for overtime pay.

### 4. Resource Reallocation

Move staff from tasks with float (E, I) to help Task D.
Assumption: Non-critical tasks can tolerate delay.

### 5. Scope Reduction (Optional)

Remove a non-essential feature in the D–E chain.
Assumption: Stakeholders agree to reduce scope to recover time.

# ✅ REQUEST 4 – Earned Value Analysis (25%)

### Provided:

- EV (Earned Value) = $300,000

- AC (Actual Cost) = $400,000

- PV (Planned Value) = $500,000

- Total Budget (BAC) = $800,000

# 1. Schedule Performance

### Schedule Variance (SV)

SV = EV – PV = 300,000 – 500,000 = –200,000
➡️ Behind schedule by $200k worth of work.

### Schedule Performance Index (SPI)

SPI = EV / PV = 300,000 / 500,000 = 0.60
➡️ Only 60% of planned work completed.

# 2. Cost Performance

### Cost Variance (CV)

CV = EV – AC = 300,000 – 400,000 = –100,000
➡️ Over budget by $100k.

### Cost Performance Index (CPI)

CPI = EV / AC = 300,000 / 400,000 = 0.75
➡️ Cost efficiency is poor.

# 3. Forecast to Complete (EAC)

Since the project is performing badly in both schedule and cost:

### EAC = BAC / CPI

= 800,000 / 0.75
= $1,066,666 (approx.)

➡️ Project will exceed budget by $266,666.

# 4. Time Forecast (Based on SPI)

Duration factor = 1 / SPI = 1 / 0.60 = 1.67

If original duration = 6 months:
Forecasted = 6 × 1.67 = 10 months

➡️ Project likely to finish 4 months late.